## Estimation - Manual
ESTIMATION - Testing Worksheet
PROJECT NAME: | Google Search Engine
ESTIMATOR:
Estimates Based upon:
DATE of Estimate | mm/dd/yyyy
Activities | Total Stroies | High | Medium | low |  | Total in HRs
| 20 | 6 | 8 | 6
Times in Hours for one person
Understand Business Requirements |  | 3 | 2.64 | 1.002 |  | 6.642
Test case writing |  | 24 | 16 | 6 |  | 46
Test case review
Stroy discussion if need
Stroy testing |  | 42 | 40 | 15 |  | 97
Regression testing
Bug/Defect Retesting |  | 24 | 16 | 6 |  | 46
Regression testing |  | 24 |  |  |  | 24
Demonstrate |  | 6 | 4 | 1.5 |  | 11.5
Bug discussion | [5 empty] | 0
Automation Scripts creation |  | 30 | 24 | 9 |  | 63
Performace testing |  | 24 | 16 | 6 |  | 46
Security testing |  | 6 | 4 | 1.5 |  | 11.5
Test Cases Updation |  | 3 | 2.64 | 1.002 |  | 6.642
Rework |  | 2 |  |  |  | 2
[5 empty] | Total in HRs | 360.284
Resource Skill |  | Little Experience | Some Experience | Extensive Experience
| Same work in Hrs | 720.568 | 540.426 | 360.284
Assuming 30 min understaging of High level story
Assuming 20 min understaging of medium level story
Assuming 10 min understaging of low level story
Assuming High level /stroy need 4 hours to create test cases
Assuming medium level /stroy need 2 hours to create test cases
Assuming low level /stroy need 1 hours to create test cases
Assuming High level /stroy need 7 hours need to test
Assuming medium llevel /stroy need 5 hours need to test
Assuming low level /stroy need 2.5 hours need to test
Assuming High level /bug need 2 hours need to test
Assuming medium level /bug need 1 hours need to test
Assuming low level /bug need 1/2 an hours need to test
Assuming one hours need for one high leven stroy for demonstrate
Assuming 1/2 an hours need for one medium leven stroy for demonstrate
Assuming 15 min need for one leow leven stroy for demonstrate
Assuming High level /stroy need 5 hours need to automate
Assuming medium llevel /stroy need 3 hours need to automate
Assuming low level /stroy need 1.5 hours need to automate
Assuming High level /stroy need 5 hours need to performance testing
Assuming medium llevel /stroy need 2 hours need to performance testing
Assuming low level /stroy need 1.5 hours need to performance testing
Assuming High level /stroy need 1 hours need for security testing
Assuming medium llevel /stroy need 2 hours need for security testing
Assuming low level /stroy need 1.5 hours need for security testing
Assuming 30 min updation of test cases of High level story
Assuming 20 min updation of test cases of medium level story
Assuming 10 min updation of test cases of low level story